## Start Here
SHOPSMART — MANUAL QA DOCUMENTATION | Final documentation for the ShopSmart frontend-only e-commerce demo
Project Scope | Manual functional testing of the product listing, user flows, and other included frontend behaviors documented in the test inventory. Backend/database behavior is outside this demo's scope.
Website | https://shopsmart-testing-demo.netlify.app/
Repository | https://github.com/janhavi46/ShopSmart-Testing-Demo-Website
Execution Result | 75 Pass, 1 Fail. One defect is logged.
Environment | Operating System: Windows 11 ¦ Browser: Desktop web browser (Google Chrome) ¦ Viewport: Browser window / screen viewport
Defect Summary | BUG-001 — Product details do not open. Status: Open. Retest Result: Not Retested.
Evidence | No screenshot or recording is attached in this workbook.
Workbook Contents | Test Scenarios; Test Cases; Defect Log; Execution Summary.
Status Definitions | Pass: observed behavior matched expected result. Fail: observed behavior did not match expected result. Blocked: execution prevented by a dependency. Not Applicable: confirmed out of scope. Needs Review: result requires clarification. Not Run: not executed.

## Test Scenarios
Scenario ID | Module | Scenario / Objective | Related Test Case IDs | Priority / Notes
TS-AUTH-008 | Login | Login with valid demo account 1; Login with valid demo account 2; Login with valid demo account 3; Login with valid demo account 4 | TC-LOGIN-001, TC-LOGIN-002, TC-LOGIN-003, TC-LOGIN-004 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-009 | Login | Reject incorrect password | TC-LOGIN-005 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-010 | Login | Reject unknown email | TC-LOGIN-006 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-011 | Login | Submit login with both fields blank; Submit login with email blank; Submit login with password blank | TC-LOGIN-007, TC-LOGIN-008, TC-LOGIN-009 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-003 | Registration | Reject malformed email during registration | TC-REGIS-010 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-002 | Registration | Submit registration with all fields blank | TC-REGIS-011 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-004 | Registration | Check password minimum/maximum rules | TC-REGIS-012 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-005 | Registration | Check mismatched password confirmation | TC-REGIS-013 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-006 | Registration | Attempt duplicate email registration | TC-REGIS-014 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-007 | Registration | Check spaces around email | TC-REGIS-015 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-013 | Session | Logout from signed-in state | TC-SESSI-016 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-014 | Session | Refresh page after login | TC-SESSI-017 | Priority: Medium ¦ Execute and record evidence.
TS-AUTH-012 | Login | Toggle password visibility | TC-LOGIN-018 | Priority: Medium ¦ Execute and record evidence.
TS-PROD-001 | Products | Verify product cards render; Check displayed product prices | TC-PRODU-019, TC-PRODU-020 | Priority: Medium ¦ Execute and record evidence.
TS-PROD-002 | Products | Open product details | TC-PRODU-021 | Priority: Medium ¦ Execute and record evidence.
TS-SEARCH-001 | Search | Search exact product name | TC-SEARC-022 | Priority: Medium ¦ Execute and record evidence.
TS-SEARCH-002 | Search | Search partial product name; Search with different letter case | TC-SEARC-023, TC-SEARC-024 | Priority: Medium ¦ Execute and record evidence.
TS-SEARCH-003 | Search | Search for no matching product | TC-SEARC-025 | Priority: Medium ¦ Execute and record evidence.
TS-SEARCH-004 | Search | Search with leading/trailing spaces; Clear search query | TC-SEARC-026, TC-SEARC-027 | Priority: Medium ¦ Execute and record evidence.
TS-FILT-001 | Filters | Apply each available category filter | TC-FILTE-028 | Priority: Medium ¦ Execute and record evidence.
TS-FILT-002 | Filters | Combine search and category filter | TC-FILTE-029 | Priority: Medium ¦ Execute and record evidence.
TS-FILT-003 | Filters | Clear/reset category filter | TC-FILTE-030 | Priority: Medium ¦ Execute and record evidence.
TS-SORT-001 | Sorting | Sort price low to high | TC-SORTI-031 | Priority: Medium ¦ Execute and record evidence.
TS-SORT-002 | Sorting | Sort price high to low | TC-SORTI-032 | Priority: Medium ¦ Execute and record evidence.
TS-SORT-003 | Sorting | Change sort option after filtering | TC-SORTI-033 | Priority: Medium ¦ Execute and record evidence.
TS-CART-001 | Cart | Add one product to cart | TC-CART-034 | Priority: Medium ¦ Execute and record evidence.
TS-CART-002 | Cart | Add two different products | TC-CART-035 | Priority: Medium ¦ Execute and record evidence.
TS-CART-003 | Cart | Add same product twice | TC-CART-036 | Priority: Medium ¦ Execute and record evidence.
TS-CART-004 | Cart | Increase quantity; Decrease quantity above minimum | TC-CART-037, TC-CART-038 | Priority: Medium ¦ Execute and record evidence.
TS-CART-005 | Cart | Prevent quantity below allowed minimum; Reject non-numeric quantity | TC-CART-039, TC-CART-040 | Priority: Medium ¦ Execute and record evidence.
TS-CART-006 | Cart | Remove one item from multi-item cart | TC-CART-041 | Priority: Medium ¦ Execute and record evidence.
TS-CART-007 | Cart | Remove last item | TC-CART-042 | Priority: Medium ¦ Execute and record evidence.
TS-CART-008 | Cart | Verify subtotal calculation; Verify total after quantity changes | TC-CART-043, TC-CART-044 | Priority: Medium ¦ Execute and record evidence.
TS-CART-009 | Cart | Refresh with items in cart | TC-CART-045 | Priority: Medium ¦ Execute and record evidence.
TS-CART-010 | Cart | Verify cart badge count | TC-CART-046 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-001 | Coupons | Apply a valid documented coupon | TC-COUPO-047 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-002 | Coupons | Reject invalid coupon | TC-COUPO-048 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-003 | Coupons | Apply empty coupon | TC-COUPO-049 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-004 | Coupons | Apply coupon with different case/spaces | TC-COUPO-050 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-005 | Coupons | Apply coupon more than once | TC-COUPO-051 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-006 | Coupons | Verify discount arithmetic | TC-COUPO-052 | Priority: Medium ¦ Execute and record evidence.
TS-COUP-007 | Coupons | Change/remove applied coupon | TC-COUPO-053 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-001 | Checkout | Open checkout with populated cart | TC-CHECK-054 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-002 | Checkout | Attempt checkout with empty cart | TC-CHECK-055 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-003 | Checkout | Submit required checkout fields blank | TC-CHECK-056 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-004 | Checkout | Validate malformed email; Validate malformed phone/postcode | TC-CHECK-057, TC-CHECK-058 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-005 | Checkout | Verify order summary | TC-CHECK-059 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-006 | Checkout | Complete simulated checkout with valid demo data | TC-CHECK-060 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-007 | Checkout | Verify confirmation details | TC-CHECK-061 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-008 | Checkout | Click submit twice quickly | TC-CHECK-062 | Priority: Medium ¦ Execute and record evidence.
TS-CHECK-009 | Checkout | Refresh/back after completion | TC-CHECK-063 | Priority: Medium ¦ Execute and record evidence.
TS-NAV-001 | Navigation | Check all visible navigation links/buttons | TC-NAVIG-064 | Priority: Medium ¦ Execute and record evidence.
TS-NAV-002 | Navigation | Click logo/home link | TC-NAVIG-065 | Priority: Medium ¦ Execute and record evidence.
TS-UI-001 | Responsive | Check desktop viewport; Check tablet viewport; Check mobile viewport | TC-RESPO-066, TC-RESPO-067, TC-RESPO-068 | Priority: Medium ¦ Execute and record evidence.
TS-UI-002 | Responsive | Check horizontal overflow | TC-RESPO-069 | Priority: Medium ¦ Execute and record evidence.
TS-UI-003 | UI | Check images and visual consistency | TC-UI-070 | Priority: Medium ¦ Execute and record evidence.
TS-UI-004 | Accessibility | Navigate using keyboard only | TC-ACCES-071 | Priority: Medium ¦ Execute and record evidence.
TS-UI-005 | Usability | Check validation/error message clarity | TC-USABI-072 | Priority: Medium ¦ Execute and record evidence.
TS-ERR-001 | Error handling | Check search no-results state | TC-ERROR-073 | Priority: Medium ¦ Execute and record evidence.
TS-ERR-002 | Error handling | Check browser console during core flow | TC-ERROR-074 | Priority: Medium ¦ Execute and record evidence.
TS-SEC-001 | Demo limitations | Confirm checkout is clearly simulated | TC-DEMOL-075 | Priority: Medium ¦ Execute and record evidence.
TS-SEC-002 | Demo limitations | Verify only demo credentials are used in testing | TC-DEMOL-076 | Priority: Medium ¦ Execute and record evidence.

## Test Cases
Test Case ID | Scenario ID | Module | Test Case / Objective | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Defect ID | Evidence / Notes
TC-LOGIN-001 | TS-AUTH-008 | Login | Login with valid demo account 1 | Logged out; login page/form available | user1@shopsmart.test / ShopTest@123 | 1. Open site. 2. Open Login. 3. Enter email/password. 4. Submit. | Login succeeds and expected signed-in state is displayed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-002 | TS-AUTH-008 | Login | Login with valid demo account 2 | Logged out | user2@shopsmart.test / TestUser@456 | Repeat valid login using account 2. | Login succeeds and correct signed-in state is displayed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-003 | TS-AUTH-008 | Login | Login with valid demo account 3 | Logged out | user3@shopsmart.test / ValidUser@789 | Repeat valid login using account 3. | Login succeeds and correct signed-in state is displayed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-004 | TS-AUTH-008 | Login | Login with valid demo account 4 | Logged out | user4@shopsmart.test / CartTest@321 | Repeat valid login using account 4. | Login succeeds and correct signed-in state is displayed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-005 | TS-AUTH-009 | Login | Reject incorrect password | Logged out | user1@shopsmart.test / WrongPass@123 | Enter valid demo email and wrong password; submit. | Login is rejected with a clear message; user is not signed in. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-006 | TS-AUTH-010 | Login | Reject unknown email | Logged out | unknown@shopsmart.test / ShopTest@123 | Enter unknown email and password; submit. | Login is rejected; no authenticated state is shown. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-007 | TS-AUTH-011 | Login | Submit login with both fields blank | Logged out | Blank email and password | Open login and submit without entering values. | Required-field validation appears or submission is prevented. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-008 | TS-AUTH-011 | Login | Submit login with email blank | Logged out | Blank email; password ShopTest@123 | Enter only password and submit. | Email validation appears or submission is prevented. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-009 | TS-AUTH-011 | Login | Submit login with password blank | Logged out | user1@shopsmart.test; blank password | Enter only email and submit. | Password validation appears or submission is prevented. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-010 | TS-AUTH-003 | Registration | Reject malformed email during registration | Registration form available | abc, abc@, abc.com | Try each malformed email with other required fields valid. | Invalid email is rejected with clear validation. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-011 | TS-AUTH-002 | Registration | Submit registration with all fields blank | Registration form available | All blank | Submit empty registration form. | Required-field validation appears or submission is prevented. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-012 | TS-AUTH-004 | Registration | Check password minimum/maximum rules | Registration form available | Passwords around displayed length limits | Try values just below, at, and above any stated limits. | Behavior matches rules displayed by the application; record actual rule. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-013 | TS-AUTH-005 | Registration | Check mismatched password confirmation | Only if confirmation field exists | Password A vs Password B | Enter different password and confirmation; submit. | Mismatch is identified and account is not created. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-014 | TS-AUTH-006 | Registration | Attempt duplicate email registration | Only if user-created registration exists; account already registered | Existing demo email | Register again using same email. | Duplicate registration is rejected or existing-account behavior is clearly explained. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-REGIS-015 | TS-AUTH-007 | Registration | Check spaces around email | Registration form available | ' user1@shopsmart.test ' | Enter email with leading/trailing spaces; submit. | Whitespace is handled consistently; no malformed/duplicate unexpected state. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SESSI-016 | TS-AUTH-013 | Session | Logout from signed-in state | Logged in | Valid demo account | Click Logout; inspect header/account state and revisit account/cart areas. | User is signed out and signed-in-only state is cleared as designed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SESSI-017 | TS-AUTH-014 | Session | Refresh page after login | Logged in | Valid demo account | Refresh browser and observe signed-in state. | Behavior matches intended demo session design; no broken/contradictory UI. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-LOGIN-018 | TS-AUTH-012 | Login | Toggle password visibility | Login form; only if toggle exists | Any demo password | Toggle visibility on/off and inspect input. | Password visibility changes correctly and toggle state is understandable. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-PRODU-019 | TS-PROD-001 | Products | Verify product cards render | Home/product listing loaded | N/A | Inspect all visible cards and scroll through list. | Product cards render without broken layout; names/prices/images are present where expected. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-PRODU-020 | TS-PROD-001 | Products | Check displayed product prices | Product listing loaded | N/A | Compare displayed prices with product details/cart values where available. | Price is consistent across listing, details, cart and summary. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-PRODU-021 | TS-PROD-002 | Products | Open product details | Only if product details are supported | Any product | Open a product card/details control. | Correct product information appears and navigation/back behavior works. | Product details did not open; detailed product information was unavailable. | Fail | BUG-001 | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-022 | TS-SEARCH-001 | Search | Search exact product name | Product listing loaded | Copy exact displayed product name | Enter exact name in search field. | Matching product appears; unrelated products are excluded. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-023 | TS-SEARCH-002 | Search | Search partial product name | Product listing loaded | Distinctive substring | Search using part of a displayed product name. | Relevant matching product(s) appear. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-024 | TS-SEARCH-002 | Search | Search with different letter case | Product listing loaded | Same name in uppercase/lowercase | Repeat search using different case. | Search behavior is consistent with intended case handling. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-025 | TS-SEARCH-003 | Search | Search for no matching product | Product listing loaded | zz-no-product-999 | Enter unlikely search term. | Clear no-results state appears; no unrelated results are shown. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-026 | TS-SEARCH-004 | Search | Search with leading/trailing spaces | Product listing loaded | ' [valid product name] ' | Search with spaces around a valid product name. | Whitespace is handled sensibly; results are not unexpectedly lost. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SEARC-027 | TS-SEARCH-004 | Search | Clear search query | A search is active | Existing search term | Clear the search field using UI or delete query. | Full product list returns, unless design specifies otherwise. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-FILTE-028 | TS-FILT-001 | Filters | Apply each available category filter | Product listing loaded | Each category shown in UI | Select one category at a time; inspect results. | All shown products match selected category; no unrelated items appear. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-FILTE-029 | TS-FILT-002 | Filters | Combine search and category filter | Search and filter controls available | Valid query + category | Enter query, then select category. | Results satisfy both active conditions or app clearly indicates supported behavior. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-FILTE-030 | TS-FILT-003 | Filters | Clear/reset category filter | A filter is active | N/A | Use clear/reset or select all/default option. | Default product list returns. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SORTI-031 | TS-SORT-001 | Sorting | Sort price low to high | At least 2 products with different prices | N/A | Select ascending price sort; inspect sequence. | Prices are in non-decreasing order. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SORTI-032 | TS-SORT-002 | Sorting | Sort price high to low | At least 2 products with different prices | N/A | Select descending price sort; inspect sequence. | Prices are in non-increasing order. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-SORTI-033 | TS-SORT-003 | Sorting | Change sort option after filtering | Filter active and sort control available | Category + price sort | Apply filter, change sort option. | Only filtered products remain and are ordered according to selected sort. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-034 | TS-CART-001 | Cart | Add one product to cart | Product listing loaded; cart empty | One available product | Click Add to Cart; open cart. | Selected product appears once with correct name and price. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-035 | TS-CART-002 | Cart | Add two different products | Product listing loaded | Two different products | Add both products; open cart. | Both products appear with correct prices and quantities. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-036 | TS-CART-003 | Cart | Add same product twice | Product listing loaded | Same product twice | Add same product twice; inspect cart lines and quantity. | App follows consistent design: quantity increments or duplicate lines are handled correctly. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-037 | TS-CART-004 | Cart | Increase quantity | Product already in cart | Quantity 1 then 2 | Use quantity increase control once. | Quantity increases by one and subtotal/total updates correctly. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-038 | TS-CART-004 | Cart | Decrease quantity above minimum | Product quantity at least 2 | Quantity 2 | Decrease quantity once. | Quantity decreases by one and totals update correctly. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-039 | TS-CART-005 | Cart | Prevent quantity below allowed minimum | Product in cart | Attempt 0 or negative only if field editable | Try setting quantity to 0/negative or decrementing at minimum. | Quantity cannot become invalid; item removal behavior is clear if minimum is reached. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-040 | TS-CART-005 | Cart | Reject non-numeric quantity | Only if quantity is editable | abc, symbols | Enter non-numeric value and leave/submit. | Invalid quantity is prevented or normalized safely; totals remain valid. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-041 | TS-CART-006 | Cart | Remove one item from multi-item cart | At least 2 products in cart | Two products | Remove one product. | Only selected item is removed; remaining item and totals are correct. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-042 | TS-CART-007 | Cart | Remove last item | One product in cart | One product | Remove item. | Empty-cart state appears; stale totals/items are not shown. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-043 | TS-CART-008 | Cart | Verify subtotal calculation | At least one item in cart | Known product price and quantity | Calculate price × quantity manually; compare subtotal. | Displayed subtotal matches item prices multiplied by quantities. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-044 | TS-CART-008 | Cart | Verify total after quantity changes | Cart with one or more products | Known quantities | Change quantities and compare totals manually. | Total updates correctly and consistently. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-045 | TS-CART-009 | Cart | Refresh with items in cart | Cart contains item | One product | Refresh page and reopen cart. | Cart persistence or clearing matches intended design; no contradictory badge/summary. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CART-046 | TS-CART-010 | Cart | Verify cart badge count | Cart badge exists | Add/remove items | Add item, change quantity, remove item; observe badge. | Badge matches intended count convention (items or total quantity) consistently. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-047 | TS-COUP-001 | Coupons | Apply a valid documented coupon | Cart has eligible item; valid coupon known from UI/README | [Enter actual valid demo coupon] | Enter valid code and apply. | Coupon is accepted and discount is displayed according to stated rules. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-048 | TS-COUP-002 | Coupons | Reject invalid coupon | Cart has item | INVALID-999 | Apply invalid code. | Coupon is rejected with clear feedback; total does not receive unintended discount. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-049 | TS-COUP-003 | Coupons | Apply empty coupon | Cart has item | Blank | Click apply without entering a code. | Empty input is handled clearly; no unexpected discount is applied. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-050 | TS-COUP-004 | Coupons | Apply coupon with different case/spaces | Cart has item | Valid code in lower case / with spaces | Apply modified formatting of valid code. | Behavior follows documented case/whitespace handling; feedback is clear. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-051 | TS-COUP-005 | Coupons | Apply coupon more than once | Cart has item | Valid coupon | Apply same code repeatedly. | Discount is not unintentionally stacked unless explicitly supported. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-052 | TS-COUP-006 | Coupons | Verify discount arithmetic | Cart has eligible subtotal | Valid coupon | Record subtotal, discount and final total; calculate manually. | Discount and final total match the coupon rule and rounding convention. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-COUPO-053 | TS-COUP-007 | Coupons | Change/remove applied coupon | Coupon applied; only if removal/change is supported | Valid then invalid/blank code | Remove or replace coupon using UI. | Old discount is removed/recalculated correctly; no stale discount remains. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-054 | TS-CHECK-001 | Checkout | Open checkout with populated cart | Cart has at least one item | Demo-only checkout data | Proceed to checkout. | Checkout loads and summary reflects cart contents. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-055 | TS-CHECK-002 | Checkout | Attempt checkout with empty cart | Cart empty | N/A | Open checkout or click checkout from empty cart. | Checkout is blocked or a clear empty-cart message is shown. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-056 | TS-CHECK-003 | Checkout | Submit required checkout fields blank | Checkout form available | All blank | Submit without entering required values. | Required field validation appears and order is not completed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-057 | TS-CHECK-004 | Checkout | Validate malformed email | Email field exists | not-an-email | Enter malformed email and submit. | Email validation appears and invalid order is not completed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-058 | TS-CHECK-004 | Checkout | Validate malformed phone/postcode | Relevant fields exist | Letters/too-short values | Enter invalid values and submit. | Field validation follows stated format requirements. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-059 | TS-CHECK-005 | Checkout | Verify order summary | Cart has multiple items and coupon if applicable | Known item quantities and discount | Proceed to checkout and compare line items, subtotal, discount, total. | Checkout summary matches cart and applied coupon calculations. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-060 | TS-CHECK-006 | Checkout | Complete simulated checkout with valid demo data | Cart populated; form available | Fictional data only | Enter safe fake test data and submit once. | Demo order completes with clear confirmation and no real payment is requested. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-061 | TS-CHECK-007 | Checkout | Verify confirmation details | Successful simulated checkout | Confirmation shown | Inspect confirmation text/order number if present. | Confirmation is clear and consistent with submitted demo order. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-062 | TS-CHECK-008 | Checkout | Click submit twice quickly | Checkout ready; only if safe and no real payment | Fictional data only | Click submit twice quickly and observe result. | No duplicate demo orders or contradictory confirmations occur. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-CHECK-063 | TS-CHECK-009 | Checkout | Refresh/back after completion | Order confirmation displayed | N/A | Refresh or navigate back once; observe state. | Behavior is consistent and does not create an unexpected duplicate order. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-NAVIG-064 | TS-NAV-001 | Navigation | Check all visible navigation links/buttons | Site loaded | N/A | Click each main navigation link/button and use browser Back. | Each control opens the correct section/state; no dead links. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-NAVIG-065 | TS-NAV-002 | Navigation | Click logo/home link | Logo link exists | N/A | Click logo and observe destination. | Returns to home/product listing as expected. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-RESPO-066 | TS-UI-001 | Responsive | Check desktop viewport | Browser at 1366x768 or similar | 1366x768 | Open site; inspect navigation, product grid, cart and forms. | Layout is readable and controls are usable without overlap. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-RESPO-067 | TS-UI-001 | Responsive | Check tablet viewport | Browser responsive tools or tablet | 768x1024 | Inspect major pages and workflows. | Layout adapts without major overlap or clipped controls. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-RESPO-068 | TS-UI-001 | Responsive | Check mobile viewport | Browser responsive tools or phone | 390x844 | Inspect navigation, product grid, cart, forms and buttons. | Content fits viewport; controls remain usable. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-RESPO-069 | TS-UI-002 | Responsive | Check horizontal overflow | Desktop, tablet and mobile widths | N/A | At each viewport, scroll horizontally if possible and inspect page edges. | No unintended horizontal scrolling or clipped content. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-UI-070 | TS-UI-003 | UI | Check images and visual consistency | Site loaded | N/A | Scroll through product cards and pages. | No broken images, overlapping elements or visibly truncated key content. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-ACCES-071 | TS-UI-004 | Accessibility | Navigate using keyboard only | Site loaded | Tab, Shift+Tab, Enter, Space, Esc | Navigate main controls without mouse. | Focus is visible and interactive controls can be reached/activated reasonably. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-USABI-072 | TS-UI-005 | Usability | Check validation/error message clarity | Forms available | Invalid test data | Trigger validation errors in login, registration and checkout. | Messages identify the issue and help user correct it. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-ERROR-073 | TS-ERR-001 | Error handling | Check search no-results state | Product listing loaded | No-match search term | Search for a non-existent product. | No-results message/state is understandable and layout remains stable. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-ERROR-074 | TS-ERR-002 | Error handling | Check browser console during core flow | Browser developer tools available | N/A | Open Console; run login/search/cart/coupon/checkout flow; note errors. | No reproducible errors affecting core workflows; log any observed errors with steps. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-DEMOL-075 | TS-SEC-001 | Demo limitations | Confirm checkout is clearly simulated | Checkout flow available | Fictional data only | Inspect checkout labels and submission outcome. | UI does not imply real payment/order fulfillment if these are not implemented. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.
TC-DEMOL-076 | TS-SEC-002 | Demo limitations | Verify only demo credentials are used in testing | Before execution | Provided fictional demo accounts | Use only documented demo accounts and fictional checkout data. | No real credentials or personal information are entered or committed. | Observed behavior matched the expected result during manual execution. | Pass | N/A — no defect observed | Manual execution completed in Windows 11 using a desktop browser at browser-window/screen viewport.

## Defect Log
Defect ID | Title | Module | Environment | Severity | Priority | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Evidence | Status | Retest Result | Notes
BUG-001 | Product details do not open | Product Listing / Product Details | Windows 11; desktop web browser; browser-window/screen viewport. Browser name/version not specified. | High | High | The ShopSmart website is open and the product listing page is displayed. | 1. Open the product listing page. 2. Select a product or its product-details action. | The selected product's detail view opens and displays its detailed information. | The product details did not open; detailed product information was unavailable. | No screenshot or recording attached. | Open | Not Retested | Observed during manual testing. Retest after the issue is fixed; attach evidence if available.

## Execution Summary
SHOPSMART — MANUAL TEST EXECUTION SUMMARY | Final counts from Test Cases sheet
Operating System | Windows 11
Browser | Desktop web browser (name/version not specified)
Viewport | Browser window / screen viewport
Test Website | https://shopsmart-testing-demo.netlify.app/
Total Test Cases | 76
Pass | 75
Fail | 1
Blocked | 0
Not Applicable | 0
Needs Review | 0
Not Run | 0
Executed (Pass + Fail) | 76
Pass Rate (Pass ÷ Executed) | 98.68%
Defects Logged | 1
Defect ID | BUG-001
Defect Title | Product details do not open
Defect Status | Open
Retest Result | Not Retested
Evidence | No screenshot or recording attached